## Dashboard
WattWise — Learning & Project Dashboard
Update task statuses in Project Tracker and learning statuses in Learning Curriculum. This sheet summarizes progress.
Metric | Value | How to interpret
Total project tasks | 66 | All planned project deliverables
Tasks done | 4 | Only mark done when acceptance criteria pass
Tasks in progress | 3 | Work currently underway
Tasks blocked | 0 | Needs a decision or dependency resolved
Project completion | 6.061% | Completed tasks / total tasks
Learning topics | 24 | Topics listed in learning curriculum
Learning topics comfortable | 0 | Topics you can explain and apply
Progress by phase
Phase | Total tasks | Done | Progress
0. Product & setup | 7 | 4 | 57.14%
1. Data model | 7 | 0 | 0%
2. Bill & reading flows | 7 | 0 | 0%
3. Calculation & reconciliation | 6 | 0 | 0%
4. Dashboard & analytics | 4 | 0 | 0%
5. Python foundations | 9 | 0 | 0%
6. Python service | 4 | 0 | 0%
7. Anomaly detection | 5 | 0 | 0%
8. Forecasting | 4 | 0 | 0%
9. Evidence-grounded LLM | 4 | 0 | 0%
10. Feedback & quality | 4 | 0 | 0%
11. Deploy & present | 5 | 0 | 0%

## Project Tracker
Phase | Task ID | Task / Deliverable | What to learn / do | Type | Priority | Depends on | Status | Acceptance criteria / Definition of Done | Completed date
0. Product & setup | WW-001 | Write project brief | Define users, problem, two input modes, key outcomes, and non-goals. | Planning | High |  | In Progress | A short README/docs brief explains what WattWise does and explicitly excludes smart-meter hardware for MVP.
0. Product & setup | WW-002 | Define user stories and demo journey | Think through adding a bill, adding readings, reconciling, viewing analytics, and reading an insight. | Planning | High | WW-001 | In Progress | At least 5 user stories and one end-to-end demo journey are written.
0. Product & setup | WW-003 | Set up Git repository | Learn/refresh Git init, commits, branches, .gitignore, and readable commit messages. | Setup | High | WW-001 | Done | Repository has meaningful first commits and no secrets or node_modules committed. | 2026-10-09
0. Product & setup | WW-004 | Create project README and folders | Create frontend, backend, analytics, database, docs folders and setup placeholders. | Setup | High | WW-003 | Done | Folder structure and README are clear enough for a new developer to follow. | 2026-10-09
0. Product & setup | WW-005 | Set up React + Vite app | Use familiar React skills; build app shell and routing. | Frontend | High | WW-004 | Done | Frontend runs locally and has a basic layout. | 2026-10-09
0. Product & setup | WW-006 | Set up Express server | Create server, route structure, middleware, JSON parsing, and GET /api/health. | Backend | High | WW-004 | Done | Health route returns predictable JSON; errors are handled cleanly. | 2026-10-09
0. Product & setup | WW-007 | Environment variables and config | Learn .env usage, config separation, and secret handling. | Setup/Security | High | WW-006 | In Progress | .env is ignored by Git; .env.example lists variable names without secrets.
1. Data model | WW-008 | Draw database ERD | Understand entities, relationships, primary keys, foreign keys, and one-to-many relationships. | Database | High | WW-001 | Not Started | Diagram includes property/household, meter, bill, meter reading, and analysis/insight entities.
1. Data model | WW-009 | Set up PostgreSQL and connection | Refresh SQL, connection config, connection pooling, and error handling using pg. | Database | High | WW-006 | Not Started | Backend connects to local PostgreSQL without hard-coded credentials.
1. Data model | WW-010 | Create migrations/schema | Learn constraints, indexes, timestamps, numeric types, and migration discipline. | Database | High | WW-008, WW-009 | Not Started | A clean database can be built from the schema/migrations.
1. Data model | WW-011 | Create properties and meters tables | Keep each reading tied to the correct household and physical meter. | Database | High | WW-010 | Not Started | Foreign keys prevent orphan meters and properties.
1. Data model | WW-012 | Create bills table | Store period dates, billed units, amount, optional opening/closing readings, actual/estimated status, and source. | Database | High | WW-010 | Not Started | Bill evidence remains separate from manual meter observations.
1. Data model | WW-013 | Create meter_readings table | Store meter ID, timestamp, cumulative value, unit, source, note, and quality status. | Database | High | WW-010 | Not Started | Manual readings preserve timestamp and meter identity.
1. Data model | WW-014 | Seed realistic synthetic data | Learn seed scripts and design cases for success and failure. | Data quality | High | WW-012, WW-013 | Not Started | Includes matching readings, mismatch, incomplete coverage, duplicate timestamp, estimated bill, and reset.
2. Bill & reading flows | WW-015 | Design monthly bill form | Plan fields, required/optional values, error messages, and date handling. | UX/Frontend | High | WW-012 | Not Started | Form clearly distinguishes billed units from opening/closing meter values.
2. Bill & reading flows | WW-016 | Implement POST/GET bills API | Learn request validation, status codes, SQL parameters, and error responses. | Backend | High | WW-012 | Not Started | Valid bills persist; malformed/invalid periods return useful 4xx responses.
2. Bill & reading flows | WW-017 | Connect monthly bill UI to API | Handle loading, success, field errors, server errors, and refresh/list view. | Full-stack | High | WW-015, WW-016 | Not Started | A bill can be created and then seen in the bill history.
2. Bill & reading flows | WW-018 | Design manual reading form | Allow meter, reading timestamp, cumulative kWh, and optional note. | UX/Frontend | High | WW-013 | Not Started | User understands that the input is a cumulative meter value, not usage for that day.
2. Bill & reading flows | WW-019 | Implement POST/GET readings API | Validate meter ID, timestamp, nonnegative numeric value, and unit. | Backend | High | WW-013 | Not Started | Valid readings persist and can be filtered by meter/date range.
2. Bill & reading flows | WW-020 | Connect manual reading UI to API | Implement loading, success/error states, history list, and correction workflow. | Full-stack | High | WW-018, WW-019 | Not Started | A user can enter and view manual readings.
2. Bill & reading flows | WW-021 | Handle duplicate and correction cases | Learn unique constraints, conflict handling, and safe edits/voids. | Database/Backend | Medium | WW-017, WW-020 | Not Started | Duplicate readings are rejected or flagged; corrections are explicit.
3. Calculation & reconciliation | WW-022 | Write usage calculation function | Cumulative interval usage = later reading − earlier reading; validate chronology and meter identity. | Backend/Logic | High | WW-019 | Not Started | Known sample readings return correct usage; negative delta is flagged.
3. Calculation & reconciliation | WW-023 | Handle reset/replacement/meter change | Model quality flags and meter lifecycle; never treat reset as negative usage. | Data quality | High | WW-022 | Not Started | Reset/replacement cases are marked for review, not silently calculated.
3. Calculation & reconciliation | WW-024 | Align reading intervals to bill dates | Learn date boundaries, interval coverage, missing gaps, and overlapping periods. | Backend/Logic | High | WW-012, WW-022 | Not Started | Only same-period, valid coverage is used for reconciliation.
3. Calculation & reconciliation | WW-025 | Build reconciliation service/API | Compare billed units against valid manual interval total; return delta, percent difference, and coverage state. | Backend | High | WW-024 | Not Started | Bill and manual totals remain separate; discrepancy triggers review.
3. Calculation & reconciliation | WW-026 | Build reconciliation UI | Show match/mismatch/incomplete coverage and explain why a comparison may be unreliable. | Frontend | High | WW-025 | Not Started | User can understand values, date coverage, and any discrepancy.
3. Calculation & reconciliation | WW-027 | Write calculation unit tests | Learn test cases and boundary testing; test matching, mismatch, gaps, duplicates, reset, and period edges. | Testing | High | WW-022, WW-025 | Not Started | All core calculation tests pass reproducibly.
4. Dashboard & analytics | WW-028 | Define summary metrics | Specify units, cost, daily average when valid, period comparison, and data completeness. | Analytics/Product | High | WW-027 | Not Started | Every metric has a formula and clear time window.
4. Dashboard & analytics | WW-029 | Build dashboard summary cards | Use React components and responsive layout; handle empty/loading/error states. | Frontend | High | WW-028 | Not Started | Cards display verified metrics with date labels.
4. Dashboard & analytics | WW-030 | Build trend charts | Learn Recharts time series, axes, tooltips, and missing-period representation. | Frontend | Medium | WW-028 | Not Started | Charts show consumption/bill trends and distinguish incomplete data.
4. Dashboard & analytics | WW-031 | Implement analytics summary endpoint | Compute values deterministically in backend/SQL; avoid LLM arithmetic. | Backend | High | WW-028 | Not Started | Dashboard values can be traced to queries and formulas.
5. Python foundations | WW-032 | Install Python and create virtual environment | Learn Python version, venv, pip, packages, and project environment. | Learning/Python | High | WW-004 | Not Started | Python script runs in isolated environment and dependencies are documented.
5. Python foundations | WW-033 | Learn Python syntax and data types | Variables, strings, numbers, booleans, lists, tuples, dictionaries, sets, loops, conditionals. | Learning/Python | High | WW-032 | Not Started | Complete small exercises without copying a full solution.
5. Python foundations | WW-034 | Learn functions, modules, exceptions | Parameters/return values, imports, exceptions, file structure, and reusable code. | Learning/Python | High | WW-033 | Not Started | Write reusable usage functions with validation and useful errors.
5. Python foundations | WW-035 | Learn files and CSV/JSON | Read/write CSV and JSON; understand structured data and encoding. | Learning/Python | Medium | WW-034 | Not Started | Can load sample readings and inspect the resulting values.
5. Python foundations | WW-036 | Learn pandas basics | Series/DataFrame, selecting rows/columns, sorting, filtering, groupby, aggregation. | Learning/Python | High | WW-035 | Not Started | Produce a consumption summary from sample data in a DataFrame.
5. Python foundations | WW-037 | Learn pandas dates and missing data | Parse timestamps, sort time series, resample, missing values, duplicates, merges. | Learning/Python | High | WW-036 | Not Started | Can identify missing intervals and summarize data by period.
5. Python foundations | WW-038 | Learn NumPy and descriptive statistics | Arrays, mean, median, standard deviation, percent change, quantiles. | Learning/Statistics | Medium | WW-036 | Not Started | Compute and explain simple usage statistics.
5. Python foundations | WW-039 | Learn pytest basics | Test functions, assertions, fixtures, parametrized tests, edge cases. | Learning/Testing | High | WW-034 | Not Started | Python calculation functions have repeatable tests.
5. Python foundations | WW-040 | Rebuild summary calculations in Python | Implement period summaries and compare output with known Node calculations. | Analytics | High | WW-037, WW-039 | Not Started | Python and Node match on documented test fixtures.
6. Python service | WW-041 | Learn FastAPI and Pydantic | Routes, schemas, request validation, response models, and docs UI. | Learning/Backend | Medium | WW-040 | Not Started | A small FastAPI app validates input and returns typed output.
6. Python service | WW-042 | Create analytics service skeleton | Add health endpoint, config, logging, and tests. | Backend/AI | Medium | WW-041 | Not Started | Service starts locally and has health/test coverage.
6. Python service | WW-043 | Expose summary/data-quality endpoints | Return period summary, coverage flags, and validation issues as JSON. | Backend/AI | High | WW-042 | Not Started | Endpoints return structured responses for normal and invalid inputs.
6. Python service | WW-044 | Connect Express to FastAPI | Learn HTTP client calls, timeouts, service failures, and internal API contracts. | Integration | Medium | WW-043 | Not Started | Express handles Python success, timeout, and unavailable-service cases.
7. Anomaly detection | WW-045 | Learn anomaly detection concepts | Baseline, threshold, outlier, false positive/negative, sensitivity, and seasonality. | Learning/ML | High | WW-038, WW-040 | Not Started | Can explain why a reading is flagged and what evidence is used.
7. Anomaly detection | WW-046 | Build transparent rule-based detector | Start with minimum-history checks, rolling median/mean, percentage change, and thresholds. | Analytics/ML | High | WW-045 | Not Started | Each anomaly includes baseline, comparison window, threshold, and quality status.
7. Anomaly detection | WW-047 | Create labelled test scenarios | Label true spikes, normal seasonal increases, missing data, resets, and data-entry errors. | Data/ML | High | WW-014, WW-046 | Not Started | Synthetic evaluation dataset covers common failure modes.
7. Anomaly detection | WW-048 | Evaluate and tune detector | Review false positives/negatives and avoid overclaiming causation. | Data/ML | High | WW-047 | Not Started | Evaluation notes document what works, what fails, and why.
7. Anomaly detection | WW-049 | Explore scikit-learn and Isolation Forest | Learn fit/predict, feature scaling where relevant, contamination, and evaluation limitations. | Learning/ML | Low | WW-048 | Not Started | Only retain ML model if it adds value beyond transparent rules.
8. Forecasting | WW-050 | Learn forecasting fundamentals | Time series, trend/seasonality, time-based split, data leakage, naive baseline. | Learning/ML | High | WW-038 | Not Started | Can explain why random train/test split is unsuitable for time series.
8. Forecasting | WW-051 | Build naive consumption forecast | Use recent average daily usage or a simple baseline; require enough history. | Analytics/ML | High | WW-050 | Not Started | Forecast is reproducible and unavailable when history is inadequate.
8. Forecasting | WW-052 | Learn forecast error metrics | MAE, RMSE, MAPE caveats (especially near zero), and held-out evaluation. | Learning/ML | Medium | WW-051 | Not Started | Model performance is compared against a naive baseline.
8. Forecasting | WW-053 | Estimate future bill cautiously | Separate predicted kWh from bill estimate; account for known tariff inputs only when implemented. | Analytics/Product | Medium | WW-052 | Not Started | UI explains assumptions and uncertainty; does not imply guaranteed bill amount.
9. Evidence-grounded LLM | WW-054 | Learn LLM API basics and prompting | Server-side calls, system instructions, input limits, temperature, and provider abstraction. | Learning/AI | Medium | WW-048, WW-052 | Not Started | Can call provider from backend without exposing API key to frontend.
9. Evidence-grounded LLM | WW-055 | Define verified-facts JSON schema | Pass computed metrics, baseline, date range, quality flags, and method metadata. | Backend/AI | High | WW-054 | Not Started | LLM receives only relevant verified facts, not raw personal identifiers.
9. Evidence-grounded LLM | WW-056 | Implement explanation adapter | Generate plain-language explanations and require “insufficient evidence” when appropriate. | Backend/AI | Medium | WW-055 | Not Started | Explanations refer to supplied evidence and do not invent appliance-level causes.
9. Evidence-grounded LLM | WW-057 | Validate output and failure handling | Validate schema, handle malformed output, timeout, rate limits, cost limits, and retries carefully. | Testing/AI | High | WW-056 | Not Started | Numeric metrics remain backend-owned and provider failure degrades gracefully.
10. Feedback & quality | WW-058 | Add insight feedback/action logging | Allow useful/not useful feedback and log actions users tried. | Full-stack | Medium | WW-057 | Not Started | Feedback is stored with the insight/analysis run.
10. Feedback & quality | WW-059 | Add end-to-end regression tests | Test bill entry → manual readings → reconciliation → dashboard → insight. | Testing | High | WW-027, WW-044, WW-057 | Not Started | Core demo journey can be repeated without manual DB fixes.
10. Feedback & quality | WW-060 | Polish accessibility and responsive UI | Keyboard navigation, labels, focus states, mobile widths, readable chart labels. | Frontend | Medium | WW-059 | Not Started | Main user flows work on desktop and mobile widths.
10. Feedback & quality | WW-061 | Add logging and error states | Use request IDs, useful server logs, safe user-facing errors, and no secret leakage. | Backend/Quality | Medium | WW-059 | Not Started | Failures can be debugged without exposing secrets or raw sensitive data.
11. Deploy & present | WW-062 | Choose deployment arrangement | Plan hosting for frontend, Express API, Python service, and PostgreSQL. | Deployment | Medium | WW-059 | Not Started | Architecture and environment variables are documented.
11. Deploy & present | WW-063 | Configure deployment and migrations | Deploy services, configure secrets, run migrations, and seed demo data. | Deployment | Medium | WW-062 | Not Started | App can be started from documented deployment instructions.
11. Deploy & present | WW-064 | Create clean demo dataset and demo account | Use synthetic data and demonstrate both input modes plus mismatch handling. | Demo | High | WW-063 | Not Started | Demo is repeatable and contains no real household personal data.
11. Deploy & present | WW-065 | Write architecture and limitations documentation | Document design decisions, evaluation, known limitations, and how to run tests. | Documentation | High | WW-064 | Not Started | A reviewer can understand and run the project from the README.
11. Deploy & present | WW-066 | Record project walkthrough | Show data entry, reconciliation, dashboard, anomaly, forecast, and evidence-backed explanation. | Portfolio | Medium | WW-065 | Not Started | Short walkthrough demonstrates real functionality rather than slides only.

## Learning Curriculum
Learning Stage | Topic | Specific subtopics to learn | Why WattWise needs it | Practice / mini-task | Related project task IDs | Status | Confidence (1-5) | Resource / notes
Python Basics | Environment setup | Python install/version, venv, pip, requirements.txt, running scripts | Keep analytics dependencies isolated from Node dependencies. | Create a venv and run a small script. | WW-032 | Not Started
Python Basics | Core syntax | Variables, numeric/string/bool types, lists, tuples, dictionaries, sets | Represent readings and structured facts. | Create a list of readings and compute a simple difference. | WW-033 | Not Started
Python Basics | Control flow | if/else, for/while loops, comprehensions, truthiness | Validate input and process sequences. | Reject an invalid reading and loop through sample readings. | WW-033 | Not Started
Python Basics | Functions | Parameters, return values, defaults, scope, docstrings | Make calculation logic reusable and testable. | Write calculate_interval_usage(previous, current). | WW-034 | Not Started
Python Basics | Errors and modules | try/except, custom errors, imports, packages, file structure | Handle invalid data and organize code. | Handle negative delta and split helpers into modules. | WW-034 | Not Started
Data formats | CSV and JSON | Read/write CSV, JSON serialization, encoding, schemas | Move sample data between app and analytics. | Load a synthetic readings CSV and emit JSON summary. | WW-035 | Not Started
Data analysis | pandas basics | Series, DataFrame, columns, filtering, sorting, groupby, aggregation | Summarize usage by day/month and inspect data. | Create a monthly consumption table. | WW-036 | Not Started
Data analysis | Dates and time series | to_datetime, sorting, time zones, date ranges, resample, interval boundaries | Align readings to billing periods and identify gaps. | Find readings within a bill's period and flag missing intervals. | WW-037 | Not Started
Data quality | Missing and duplicate data | isna, duplicates, invalid values, merge validation, missing intervals | Prevent misleading totals and comparisons. | Create a quality report for sample readings. | WW-037 | Not Started
Statistics | Descriptive statistics | Mean, median, range, standard deviation, quantiles, percentage change | Build transparent baselines and comparisons. | Compare current use with previous complete periods. | WW-038 | Not Started
Testing | pytest basics | Assertions, fixtures, parametrization, test discovery, edge cases | Ensure calculations are trustworthy. | Test matching, discrepancy, reset, and missing-data examples. | WW-039 | Not Started
APIs | FastAPI basics | Routes, HTTP methods, status codes, Pydantic models, docs | Expose Python analysis to the Node backend. | Create a POST endpoint with a validated request model. | WW-041 | Not Started
APIs | Service integration | HTTP requests, timeouts, retries, error contracts, logging | Connect Express to the Python service reliably. | Make Express call Python and handle a stopped Python service. | WW-044 | Not Started
ML Foundations | ML vocabulary | Features, labels, training vs inference, baseline, overfitting, leakage | Understand what models do and where they can fail. | Explain features/labels for an anomaly dataset. | WW-045 | Not Started
Anomaly detection | Rule-based methods | Rolling mean/median, thresholds, percent change, minimum history | Create an interpretable first detector. | Flag a synthetic spike and explain its baseline. | WW-046 | Not Started
Anomaly detection | Evaluation | True/false positives, false negatives, precision/recall basics, labelled cases | Measure whether alerts are useful. | Evaluate detector against labelled synthetic cases. | WW-048 | Not Started
scikit-learn | Isolation Forest basics | fit, predict, contamination, features, model limitations | Explore an ML alternative only if rules are insufficient. | Compare it against rule-based alerts on synthetic data. | WW-049 | Not Started
Forecasting | Time-series fundamentals | Trend, seasonality, naive baseline, time-based split, data leakage | Forecast future consumption responsibly. | Create a baseline forecast using prior periods. | WW-050, WW-051 | Not Started
Forecasting | Error metrics | MAE, RMSE, MAPE limitations, held-out evaluation | Report forecast performance rather than guessing. | Score forecasts against held-out periods. | WW-052 | Not Started
LLM integration | Prompt design | Clear task, evidence-only constraints, uncertainty, avoid causal assumptions | Explain metrics without inventing reasons. | Write a prompt using a JSON facts object. | WW-054, WW-055 | Not Started
LLM integration | Structured output and validation | JSON schema, parsing, validation, malformed output, refusals | Keep generated text safe and consistent with computed facts. | Reject an explanation that changes the supplied unit count. | WW-057 | Not Started
LLM operations | Secrets, cost and reliability | Server-only API keys, timeouts, rate limits, token/cost limits, privacy | Avoid leaked keys and uncontrolled costs. | Add env config and simulated provider-failure test. | WW-054, WW-057 | Not Started
Engineering | Git and documentation | Branches, commits, README, architecture diagram, decision log | Make work maintainable and presentable. | Write a meaningful commit and document one design decision. | WW-003, WW-065 | Not Started
Quality | End-to-end testing | API tests, integration tests, regression, clean setup, demo data | Prove the full user journey works. | Run bill → readings → reconciliation → dashboard scenario. | WW-059, WW-064 | Not Started

## Daily Log
Date | Session goal (one main task) | Task ID(s) | What I actually did | What worked / evidence | What I learned | Problem / blocker | Next action | Time spent (optional) | Session rating (1-5)

## Decisions & Risks
Type | Topic | Decision / risk | Mitigation / next action | Status | Notes
Decision | Input modes | Support Monthly Bill Mode and Manual Meter Mode. No smart-meter hardware in initial version. | Keep bill and manual reading data separate in database and UI. | Agreed
Decision | Billing reference | Bill remains billing reference; manual readings are additional observations. | Reconcile only aligned periods and flag mismatch for review. | Agreed
Decision | Calculation truth | All arithmetic and metrics are computed by code, not by LLM. | Add tests and show evidence for each insight. | Agreed
Decision | AI sequence | Rule-based anomaly detection and naive forecast before advanced ML. | Evaluate on labelled synthetic data before adding complexity. | Agreed
Risk | Sparse data | Monthly data may be too sparse for detailed anomaly detection or forecasting. | Require minimum history and show insufficient-data states. | Open
Risk | Period mismatch | Manual readings may not cover exact billing period. | Track coverage; do not compare totals if incomplete. | Open
Risk | Meter reset/replacement | Cumulative reading may decrease after a reset or meter change. | Flag for review and maintain meter identity/lifecycle. | Open
Risk | LLM hallucination | LLM may invent cause or alter numbers. | Pass verified facts only; validate output; never infer appliance causes without evidence. | Open
Risk | Privacy and API cost | Bills and usage patterns can be sensitive; LLM calls can incur cost. | Use synthetic demo data, keep keys server-side, minimize identifiers, add limits. | Open

## How to Use
Step | How to use this tracker
1. Start at Dashboard | Check the overall progress. Formulas update from the other sheets when opened in Excel or LibreOffice.
2. Choose the next project task | In Project Tracker, follow dependencies. Pick one main task per work session; do not start later phases just because they look exciting.
3. Update status honestly | Not Started = untouched; In Progress = active; Blocked = cannot proceed; Done = acceptance criteria passed; Skipped = deliberately removed from scope.
4. Record notes | Use Notes / Blocker for bugs, decisions, and the next small step. Avoid duplicate task rows.
5. Learn alongside building | Use Learning Curriculum to track each concept; mark Comfortable only when you can explain it and apply it without copying blindly.
6. Daily log | At the end of each session, add one row in Daily Log: goal, what you did, evidence, learning, blocker, next action.
7. Weekly review | Once a week, review completed tasks, blockers, upcoming dependencies, and whether target dates still make sense.
8. Completion rule | A task is done only when its acceptance criteria are met and relevant tests/manual checks pass.
9. No fixed timeline | There are no forced dates. Fill in Start/Target dates only if they help you plan.
10. Suggested first steps | Start with WW-001 to WW-007. Then design the schema and seed data before building advanced AI.
Status definitions | Not Started ¦ In Progress ¦ Blocked ¦ Done ¦ Skipped
Core WattWise rule | Bill = billing reference; manual readings = additional observations. Compare only aligned periods; show discrepancies rather than silently correcting.